## Sayfa1
No | Yapılacak İşler | Tarih | Sorumlu | Gerekli Yan Aksiyon
1 | Çizilecek Elemanların ve LOD Seviyelerinin Belirlenmesi | 2022-11-02 | ALL | Toplantıda Birlikte Yapılabilir. Modellenecek Elemanlar ve LoD Seviyeleri Excel'de listenebilir.
2 | Rollerin Belirlenmesi | 2022-11-02 | ALL | Toplantıda Birlikte Yapılabilir
3 | Forking Kısmı Klasörlemenin Gözden Geçirilmesi ve BEP'de gösterelim | 2022-11-04 |  | Görev Paylaşımı ile yapılabilir ve arada sunularak feedback alınabilir
4 | BEP'in hazırlanması (çakışma detaylarını unutma) | 2022-11-05 | ALL | Görev Paylaşımı ile yapılabilir ve arada sunularak feedback alınabilir
5 | Statik Projenin Temizlenmesi | 2022-11-03 | GELECEK | Görev Paylaşımı ile yapılabilir ve arada sunularak feedback alınabilir
6 | Mimari Projelerin Temizlenmesi | 2022-11-03 | GELECEK | Görev Paylaşımı ile yapılabilir ve arada sunularak feedback alınabilir
7 | Mekanik Kanal Projesinin Temizlenmesi | 2022-11-04 | GELECEK | Görev Paylaşımı ile yapılabilir ve arada sunularak feedback alınabilir
8 | Metrajların Çıkarılması (Excel) | 2022-11-04 |  | Görev Paylaşımı ile yapılabilir ve arada sunularak feedback alınabilir
9 | İş Programının Hazırlanması (P6) | 2022-11-05 |  | Görev Paylaşımı ile yapılabilir ve arada sunularak feedback alınabilir
10 | Bütçe Hazırlanabilir (Excel) | 2022-11-05 |  | Görev Paylaşımı ile yapılabilir ve arada sunularak feedback alınabilir
No | Yapılacak İşler | Tarih | Sorumlu | Gerekli Yan Aksiyon
1 | CAD 'lerini ayrı hale getirilmesi |  | MSS
2 | Klasörleme |  | ALE
3 | GitHub Devreye Alınması |  | ALL
4 | BEP tamamlanması |  | ERY
5
No | Yapılacak İşler | Tarih | Sorumlu | Gerekli Yan Aksiyon
1 | SECTION A: DESCRIPTION OF BIM EXECUTION PLAN |  | +
2 | SECTION B: PROJECT INFORMATION |  | +
3 | SECTION C: PROJECT GOALS / BIM USES |  | +
4 | SECTION D: BIM AND ORGANIZATIONAL ROLES, RESPONSIBILITIES |  | +
5 | SECTION E: BIM PROCESS DESIGN |  | ALE
6 | SECTION F: BIM INFORMATION EXCHANGES |  | ALE
| 1. LIST OF INFORMATION EXCHANGE WORKSHEET(S): ATTACHMENT 4 |  | MSS
7 | SECTION G: MODEL STRUCTURE |  | ALE
| Dosyalama ağacı şeması |  | ALE
8 | SECTION H: COMMON DATA ENVIRONMENT |  | ALE | Şeması
9 | SECTION I: DATA SEGREGATION and FEDERATION STRATEGY |  | ALE | BIM Infor. Exh. İle birleşebilir
10 | SECTION J: COLLABORATION PROCEDURES |  | ALE
11 | SECTION K: QUALITY CONTROL |  | +
12 | SECTION L: TECHNOLOGICAL INFRASTRUCTURE NEEDS |  | +
13 | SECTION M: PROJECT ORIGIN POINT and COORDINATES |  | +
14 | SECTION N: ATTACHMENTS |  | ERY
Formulas:
Tarih = +[Tarih, row above]+2
Tarih = +[Tarih, row above]

## Sayfa2
The four steps within the procedure include
1 | Identify high-value BIM uses during project planning and design phases | Proje planlama ve tasarım aşamalarında yüksek değerli BIM kullanımlarını belirleyin
2 | Design the BIM execution process by creating process maps | Süreç haritaları oluşturarak BIM yürütme sürecini tasarlayın
3 | Define the BIM deliverables in the form of information exchanges | BIM çıktılarını bilgi alışverişi şeklinde tanımlayın
4 | Develop the infrastructure in the form of contracts, communication procedures, technology, and quality control to support the implementation | Uygulamayı desteklemek için sözleşmeler, iletişim prosedürleri, teknoloji ve kalite kontrol şeklinde altyapıyı geliştirmek

## Sayfa3
|  |  | Alan : | 1920 |  | X39-X44 - Y12-Y18 Aksları arası
|  |  | Proje Adı : | IZU |  | 18 Yoğun Bakım Odası
- Total Construction Area: (Y12-Y18 – X39-X44) 1920 m² in 631,320 m² - In Main Hospital facility, MT2&3 block Floor 4th – 5th
Base Point
| Modeller |  |  | Y12-X38 = 0.00;0.00
A | Statik | 1.1 | Kolon | 1.1-Statik-Kolon | LOD300 | HOL | MT2-04-099 | #REF!
A | Statik | 1.2 | Kiriş | 1.2-Statik-Kiriş | LOD300 | BAY ASEPSİ | MT2-04-098
A | Statik | 1.3 | Döşeme | 1.3-Statik-Döşeme | LOD300 | WC PERSONEL BAYAN | MT2-04-097
A | Statik | 1.4 | Perde Duvar | 1.4-Statik-Perde Duvar | LOD300 | WC PERSONEL BAY | MT2-04-096
B | Mimari | 2.1 | Duvar - Alçıpan | 2.1-Mimari-Duvar - Alçıpan | LOD300 | BAYAN ASEPSİ | MT2-04-095
B | Mimari | 2.2 | Duvar - Bims | 2.2-Mimari-Duvar - Bims | LOD300 | ZİYARETÇİ ASEPSİ | MT2-04-094
B | Mimari | 2.3 | Otomatik Kapı | 2.3-Mimari-Otomatik Kapı | LOD300 | HOL | MT2-04-093
B | Mimari | 2.4 | Pencere | 2.4-Mimari-Pencere | LOD300 | HOL | MT2-04-100
B | Mimari | 2.5 | Yatak | 2.5-Mimari-Yatak | LOD200 | FİLTRE | MT2-04-092
B | Mimari | 2.6 | Cephe Kaplama | 2.6-Mimari-Cephe Kaplama | LOD200 | BİLGİLENDİRME OFİSİ | MT2-04-101
B | Mimari | 2.7 | Zemin-PVC + Self Lev | 2.7-Mimari-Zemin-PVC + Self Lev | LOD300 | MALZEME EKİPMAN | MT2-04-091
B | Mimari | 2.8 | Zemin-Seramik | 2.8-Mimari-Zemin-Seramik | LOD300 | MALZEME EKİPMAN | MT2-04-090
B | Mimari | 2.9 | Zemin-Parke | 2.9-Mimari-Zemin-Parke | LOD300 | TEK YATAKLI YB ODASI | MT2-04-089
B | Mimari | 2.10 | Asma Tavan | 2.10-Mimari-Asma Tavan | LOD200 | TEK YATAKLI YB ODASI | MT2-04-087
C | Mekanik | 3.1 | Havalandırma - Kanal | 3.1-Mekanik-Havalandırma - Kanal | LOD200 | TEK YATAKLI YB ODASI | MT2-04-086
C | Mekanik | 3.2 | Havalandırma - Menfez | 3.2-Mekanik-Havalandırma - Menfez | LOD200 | TEK YATAKLI YB ODASI | MT2-04-084
C | Mekanik | 3.3 | Medikal Gaz Borulama | 3.3-Mekanik-Medikal Gaz Borulama | LOD200 | KORİDOR | MT2-04-083
C | Mekanik | 3.4 | Hastabaşı Ünitesi | 3.4-Mekanik-Hastabaşı Ünitesi | LOD200 | TEK YATAKLI YB ODASI | MT2-04-081
D | Elektrik | 4.1 | Kablo Taşıyıcı Kanal | 4.1-Elektrik-Kablo Taşıyıcı Kanal | LOD200 | TEK YATAKLI YB ODASI | MT2-04-078
[6 empty] | TEK YATAKLI YB ODASI | MT2-04-077
[6 empty] | TEK YATAKLI YB ODASI | MT2-04-076
[6 empty] | TEK YATAKLI YB ODASI | MT2-04-075
[6 empty] | KORİDOR | MT2-04-105
[6 empty] | HEMŞİRE İSTASYONU | MT2-04-104
[6 empty] | PERSONEL DİNLENME | MT2-04-107
[6 empty] | İLAÇ MAHALİ | MT2-04-106
[6 empty] | TEMİZ ÇLŞ. | MT2-04-103
[6 empty] | KİRLİ MALZEME | MT2-04-102
[6 empty] | YANGIN HOLÜ | MT2-04-018
[6 empty] | M18 MERDİVENİ | MT2-04-019
ASEPSİ BAY
ASEPSİ BAYAN
ASEPSİ ZİYARETÇİ
BİLGİLENDİRME OFİSİ
FİLTRE
HEMŞİRE İSTASYONU
HOL
HOL
HOL
İLAÇ MAHALİ
KİRLİ MALZEME
KORİDOR
KORİDOR
M18 MERDİVENİ
MALZEME EKİPMAN
MALZEME EKİPMAN
PERSONEL DİNLENME
TEK YATAKLI YB ODASI
TEK YATAKLI YB ODASI
TEK YATAKLI YB ODASI
TEK YATAKLI YB ODASI
TEK YATAKLI YB ODASI
TEK YATAKLI YB ODASI
TEK YATAKLI YB ODASI
TEK YATAKLI YB ODASI
TEK YATAKLI YB ODASI
TEMİZ ÇLŞ.
WC PERSONEL BAY
WC PERSONEL BAYAN
YANGIN HOLÜ

## Çakışma Matrisi
|  | STATİK |  |  |  | MİMARİ | [6 empty] | MEKANİK |  | ELEKTRİK
ÇAKIŞMA MATRİSİ |  | Kolon | Kiriş | Döşeme | Perde Duvar | Duvar | Kapı | Pencere | Yatak | Cephe | Zemin | Tavan | Hav. Kanalı | Medikal Gaz Boruları | Kablo Taşıyıcı Kanal
STATİK | Kolon
Kiriş
Döşeme
Perde Duvar
MİMARİ | Duvar
Kapı
Pencere
Yatak
Cephe
Zemin
Tavan
MEKANİK | Havalandırma Kanalı
Medikal Gaz Boruları
ELEKTRİK | Kablo Taşıyıcı Kanal
|  |  |  | Disiplinler arası çakışmalar 1. öncelik, disipliniçi çakışmalar 2. öncelik olarak değerlendirilmiştir. | [9 empty] | 1. Öncelik
2. Öncelik

## Sayfa5
PROJECT NAME | DISCIPLINE CODE | TYPE CODE | TYPE DEFINITION | FLOOR | ORIGINATOR CODE | DESCRIPTION (Optional) | NUMBER (Optional)
IZU | ALL | D | Drawing | L4 | ALE | (Text, ex. BEP or ToDoList) | 0
| ARC | G | Diagram | L5 | ERY
| ELC | I | Image | LA | MSS
| MEC | L | List |  | UCK
| STR | M | Model
|  | T | Textual
|  | V | Video/Audio
|  | DP | Drawing Plan
|  | DE | Drawing Elevation
|  | DS | Drawing Section
|  | M2 | 2D Model File
|  | M3 | 3D Model File
|  | AF | Animation file (of a model)
|  | CM | Combined model
|  | CR | Specific for the Clash Process
|  | MR | Model rendition file for other renditions
|  | VS | Visualization file (of a model)
|  | BQ | Bill of quantities
|  | CA | Calculations
|  | CO | Correspondence
|  | CP | Cost plan
|  | DB | Database
|  | FN | File Note
|  | IE | Information exchange file
|  | MI | Minutes / action notes
|  | MS | Method statement
|  | PP | Presentation
|  | PR | Programme
|  | RD | Room data sheet
|  | RI | Request for information
|  | RP | Report
|  | SH | Schedule
|  | SP | Specification

## Sayfa6
Modeller
Base Point | Y12-X38 = 0.00;0.00
A | Statik | 1.1 | Kolon | LOD300 | 1.1-Statik-Kolon | LOD300 | Kolon
A | Statik | 1.2 | Kiriş | LOD300 | 1.2-Statik-Kiriş | LOD300 | Kiriş
A | Statik | 1.3 | Döşeme | LOD300 | 1.3-Statik-Döşeme | LOD300 | Döşeme
A | Statik | 1.4 | Perde Duvar | LOD300 | 1.4-Statik-Perde Duvar | LOD300 | Perde Duvar
B | Mimari | 2.1 | Duvar - Alçıpan | LOD300 | 2.1-Mimari-Duvar - Alçıpan | LOD300 | Duvar - Alçıpan
B | Mimari | 2.2 | Duvar - Bims | LOD300 | 2.2-Mimari-Duvar - Bims | LOD300 | Duvar - Bims
B | Mimari | 2.3 | Otomatik Kapı | LOD300 | 2.3-Mimari-Otomatik Kapı | LOD300 | Otomatik Kapı
B | Mimari | 2.4 | Pencere | LOD300 | 2.4-Mimari-Pencere | LOD300 | Pencere
B | Mimari | 2.5 | Yatak | LOD200 | 2.5-Mimari-Yatak | LOD200 | Yatak
B | Mimari | 2.6 | Cephe Kaplama | LOD200 | 2.6-Mimari-Cephe Kaplama | LOD200 | Cephe Kaplama
B | Mimari | 2.7 | Zemin-PVC + Self Lev | LOD300 | 2.7-Mimari-Zemin-PVC + Self Lev | LOD300 | Zemin-PVC + Self Lev
B | Mimari | 2.8 | Zemin-Seramik | LOD300 | 2.8-Mimari-Zemin-Seramik | LOD300 | Zemin-Seramik
B | Mimari | 2.9 | Zemin-Parke | LOD300 | 2.9-Mimari-Zemin-Parke | LOD300 | Zemin-Parke
B | Mimari | 2.10 | Asma Tavan | LOD200 | 2.10-Mimari-Asma Tavan | LOD200 | Asma Tavan
C | Mekanik | 3.1 | Havalandırma - Kanal | LOD200 | 3.1-Mekanik-Havalandırma - Kanal | LOD200 | Havalandırma - Kanal
C | Mekanik | 3.2 | Havalandırma - Menfez | LOD200 | 3.2-Mekanik-Havalandırma - Menfez | LOD200 | Havalandırma - Menfez
C | Mekanik | 3.3 | Medikal Gaz Borulama | LOD200 | 3.3-Mekanik-Medikal Gaz Borulama | LOD200 | Medikal Gaz Borulama
C | Mekanik | 3.4 | Hastabaşı Ünitesi | LOD200 | 3.4-Mekanik-Hastabaşı Ünitesi | LOD200 | Hastabaşı Ünitesi
D | Elektrik | 4.1 | Kablo Taşıyıcı Kanal | LOD200 | 4.1-Elektrik-Kablo Taşıyıcı Kanal | LOD200 | Kablo Taşıyıcı Kanal

## Sayfa6 (2)
Discipline Code | Discipline | Element Class | Element | Omniclass Code | LOD Level | Description
STA | Statical | 1.1 | Column | 21-02 10 10 10 12 | LOD300 | Specific sizes and locations of main concrete structural members modeled per defined structural grid with correct orientation | Models
STA | Statical | 1.2 | Beam | 21-02 10 10 10 12 | LOD300 | Specific sizes and locations of main concrete structural members modeled per defined structural grid with correct orientation |  | Base Point
STA | Statical | 1.3 | Slab | 21-02 10 10 10 12 | LOD300 | Specific sizes and locations of main concrete structural members modeled per defined structural grid with correct orientation |  | Y12-X38 = 0.00;0.00
STA | Statical | 1.4 | Shear Wall | 21-02 10 10 10 12 | LOD300 | Specific sizes and locations of main concrete structural members modeled per defined structural grid with correct orientation
ARC | Architectural | 2.1 | Wall - Gypsum Board | 21-03 10 10 10 | LOD300 | Wall elements are modeled to specific layouts, locations, heights, and elevation profiles. Penetrations are modeled to nominal dimensions for major wall openings such as windows, doors, and large mechanical elements.
ARC | Architectural | 2.2 | Wall - Pumice | 21-03 10 10 10 | LOD300 | Wall elements are modeled to specific layouts, locations, heights, and elevation profiles. Penetrations are modeled to nominal dimensions for major wall openings such as windows, doors, and large mechanical elements.
ARC | Architectural | 2.3 | Sliding Door | 21-03 10 30 25 | LOD300 | Units are modeled based on specified location and nominal size. Outer geometry of door frame elements modeled.
ARC | Architectural | 2.4 | Window | 21-03 10 20 20 | LOD300 | Units are modeled based on specified location and nominal size. Outer geometry of window frame elements and glazing modeled.
ARC | Architectural | 2.5 | Patient Bed | 21-05 20 50 | LOD200 | Generic model elements with approximate nominal size.
ARC | Architectural | 2.6 | Curtain Wall | 21-02 20 20 30 | LOD200 | Overall window wall assembly depth represented by a single model object.
ARC | Architectural | 2.7 | Floor - PVC | 21-03 20 30 30 | LOD300 | Single model element by type with overall thickness that accounts for materials based on specific types
ARC | Architectural | 2.8 | Floor - Tile | 21-03 20 30 20 | LOD300 | Single model element by type with overall thickness that accounts for materials based on specific types
ARC | Architectural | 2.9 | Floor - Parquet | 21-03 20 30 45 | LOD300 | Single model element by type with overall thickness that accounts for materials based on specific types
ARC | Architectural | 2.10 | Suspended Ceiling | 21-03 10 70 20 | LOD200 | Generic assemblies indicative of overall scope and approximate thickness/system depth of suspended ceiling.
MEC | Mechanical | 3.1 | Ventilation - Duct (supply air only) | 21-04 30 60 10 | LOD300 | Modeled as design-specified size, shape, spacing, and location of duct, dampers, fittings, and insulation for risers, mains, and branches.
MEC | Mechanical | 3.2 | Medical Gas Piping | 21-04 20 60 30 | LOD200 | Schematic layout of generic model elements with approximate size, shape, and location of elements.
MEC | Mechanical | 3.3 | Bedside Unit | 21-05 10 40 20 | LOD200 | Schematic layout with approximate size, shape, and location of equipment.
ELC | Electrical | 4.1 | Cable Tray | 21-04 50 20 90 | LOD300 | Modeled as design-specified size, shape, spacing, and location of raceways, boxes, enclosures, and the electrical equipment and end-devices served.
|  |  |  | reference: | LEVEL OF DEVELOPMENT (LOD) SPECIFICATION PART I & COMMENTARY (BIM FORUM 2020)

## IE Charts
LIST Of Information Exchange Worksheet Attch 4
MODEL DEFINITION WORKSHEET: Attch 5

## Sayfa7
Görseller
Tüm 3D
Birer tane 3D